## Sheet1
Milestone 5
Milestones |  | Description: | Deadline
Network Setup/ Front-end complete |  | Setup the entire network and link every pages together so that it actually gives a feel of an application | 2020-11-11
Progress Update |  | Milestone-6 for the progress update | 2020-11-17
Back-End Complete |  | Back-end complete, which has sessions, chats for all the users, and some functionalities to modify the settings | 2020-11-25
Testing/Debugging |  | Debugging the entire apllication so that eveything works well. | 2020-12-05
Final Presentation |  | Milestone-7 Final Presentation | 2020-12-11
Categories: | Tasks | Description | Assigned to: | Deadline
Front-End Development |  |  |  | 2020-11-05
| Login Form, Making it similar | Making the login page similar to the other pages | Sachin | 2020-11-05
| Modify settings page | Adding more functionalities in the settings page. | Shristi | 2020-11-05
| Chatbox for different users | Making sure that there is just one page to chat with every users | Kinsey, Khan | 2020-11-05
| Link every pages together | Making sure we can efficiently navigate our whole application | Shristi | 2020-11-05
Network Setup |  |  |  | 2020-11-09
| Figure out to setup a network within computers | Setting up our custom ports for communication between our computers | Khan, Kinsey | 2020-11-09
|  | Connecting our computer on the same network using the ip address of the host | Everyone | 2020-11-09
|  | If nothing works out, web host will be for the last option which will definitely help in communication between the computers. | Everyone | 2020-11-09
Back-End Development |  |  |  | 2020-11-20
| Store login/ signup credentials, sessions | Start sessions and look for ways to store the login and signup credentials in the database. | Sachin | 2020-11-20
| Updating account settings | Accessing the information of users from sigup/ login and also making sure they can update those. | Shristi | 2020-11-20
| Storing messages in the database | Store every messages in a file/ database, and also fetching those to see the history of messages for all people. | Khan, Kinsey | 2020-11-20
Encrytion/ Decryption |  |  |  | 2020-11-10
| Encrypting Passwords | Encryting the passwords to avoid the admin to login as any users | Shristi, Sachin | 2020-11-10
| Encrypting Messages | Encrypting messages so that not even admin can see what the private messages are between two users on the application | Khan | 2020-11-10
Debugging/Testing | Debugging the entire network application | Debug our individual pages, and everyone meets virtually to see everything works as expected. | Everyone | 2020-12-01